## Cost
# | Equipment/Package | Budget | Actual | Flag | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | Supply |  |  |  | Erection & Commissioning
| (A) Power Plant | Rs Lacs | Rs Lacs |  | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | Supplier | Order No & date | Amount (Rs Lacs) | Order Sl No. | Supplier | Order No & date | Amount (Rs Lacs) | Order Sl No.
1 | Boiler & Auxiliaries | 2865.91 | 2865.91 | [7 empty] | 573.182 |  |  |  | 286.591 | 286.591 | 286.591 | 286.591 | 286.591 | 286.591 | 286.591 | 286.591 | Isgec John Thompson | RCM/PUR/LOI/TGBOILER/06 dated February 4, 2006 | 2711.63 | 1 | Isgec Covema Ltd | RCM/PUR/LOI/BOILER/E&C/06 dated February 4, 2006 | 154.28 | 2
2 | TG & Auxiliaries | 1982.922 | 1948.07 | [7 empty] | 99.1461 | [8 empty] | 1487.1915 | 198.2922 | 198.2922 | Greenesol | RCM/PUR/ORDER/TG-3/06 dated February 15, 2006 | 1898.48 | 3 | Greenesol | RCM/PUR/ORDER/Turbine/06/E&C dated February 20, 2006 | 49.59 | 4
3 | Bagasse & Conventional Ash Handling System | 200 | 233.73 | 1 | [8 empty] | 20 |  | 26.6667 | 26.6667 | 26.6667 | 26.6667 | 26.6667 | 26.6667 |  | 20 | Masyc | RCM/PUR/ORDER/F&AHS-MASYC/06 dated June 15, 2006 | 221.61 |  | Elcoma | RCM/PUR/ORDER/F&AHS-MASYC/06 dated October 20, 2006 | 12.12
4 | Dense Phase Ash Handling System | 60 | 61.5 | 1 | [8 empty] | 6 |  | 8 | 8 | 8 | 8 | 8 | 8 |  | 6 | Macawber | RCM/PUR/ORDER/Ash/06 dated May 2, 2006 | 55.5 |  | Macawber | RCM/PUR/ORDER/Ash Handling/E&C/06 dated May 4, 2006 | 6
5 | HP Feed Water Heater | 46.6046 | 45.36 | [8 empty] | 3.95 | 2.3302 | [5 empty] | 34.9534 | 5.3709 |  |  | Larsen & Tourbo | RCM/PUR/ORDER/HEATER/06 dated March 22, 2006 | 45.36
6 | EOT Crane | 40 | 46.87 | 1 | [9 empty] | 8 |  |  | 28 | 4 |  |  |  |  | Grip | RCM/PUR/ORDER/EOTCrane/06 dated June 16, 2006 | 44.63 |  | Grip | RCM/PUR/ORDER/EOTCrane/E&C/06 dated June 17, 2006 | 2.24
7 | Water Treatment Plant | 160 | 91.69 | 1 | [9 empty] | 16 |  |  |  | 64 | 64 |  | 16 |  | Triveni | RCM/PUR/Purchase Order/WTP/06 dated August 27, 2006 | 89.45 |  | Triveni | RCM/PUR/Order/WTP/E&C/06 dated August 27, 2006 | 2.24
8 | Piping, Valves, Supports | 100 | 204.29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 20 | 20 | 10 | 10 | 0 | 0
8.1 | Piping Package & Tanks | 100 | 180.6 | 1 | [18 empty] | Southern Engg | RCM/PUR/PO/Piping/06 dated October 18, 2006 | 180.6
8.2 | Gate, Globe & Check Valves |  | 10.81 | [19 empty] | Steel Strong | RCM/PO/06/ValvesGGC/01 dated July 17, 2006 | 10.81
8.3 | Butterfly Valves |  | 9.42 | [19 empty] | Stafford | RCM/PO/06/ValvesBFY/01 dated July 14, 2006 | 9.42
8.4 | Metallic Bellows |  | 2.39 | [19 empty] | Precise Engineers | DCM/PO/06/700 NB Metallic Expansion Bellows/01 dated December 17, 2006 | 2.39
8.5 | Spring Hangers |  | 1.07 | [19 empty] | Spring Supports | Purchase Order/Spring Hanger Assembley/01 dated December 16, 2006 | 1.07
9 | Air Compressor & Dryer | 23.8088 | 23.64 | [9 empty] | 2.3809 |  |  |  | 19.047 | 2.3809 |  |  |  |  | Chicago Pneumatics | RCM/PUR/LOI/COMPRESSOR/06 dated February 25, 2006 | 23.64
10 | A/C & Ventilation | 10 | 33.69 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0
10.1 | Air Conditioning System | 5 | 7.59 | [11 empty] | 1 |  | 1 | 1 | 1 | 1 |  |  | Hitachi | RCML/PO/06/ACHitachi/01 dated September 13, 2006 | 4 |  | Spectrum | RCML/PO/06/ACSpectrum/01 dated September 13, 2006 | 3.59
10.2 | Ventilation System | 5 | 26.1 | [11 empty] | 1 |  | 1 | 1 | 1 | 1 |  |  | Pioneer | RCM/PO/06/Ventilation/01 dated September 22, 2006 | 26.1
11 | Fire fighting System | 10 | 55.44 | 1 | [9 empty] | 1 |  | 2 | 2 | 2 | 2 | 1 |  |  | Helio | RCM/PO/06/Firefighting/01 dated November 17, 2006 | 55.44
12 | Power Evacuation | 857.0008 | 908.58 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.65 | 37.7001 | 12.7001 | 0 | 20.6376 | 20.6376 | 245.6376 | 20.6376 | 0 | 181.4001 | 0 | 0
12.1 | Transmission Line & Bay | 480 | 464.3 | 1 | [7 empty] | 317.65 | [8 empty] | 162.35 |  | UP Power Corporation | Reference Letter No: 387/ETDS dated March 10,2006 | 464.3
12.2 | Switchyard | 127.0008 | 127 | [9 empty] | 12.7001 | 12.7001 |  | 20.6376 | 20.6376 | 20.6376 | 20.6376 |  | 19.0501 |  | Bharat Bijlee | RCM/PUR/LOI/Switch Yard/06 dated February 24, 2006 | 115 |  | Bharat Bijlee | RCM/PUR/LOI/Switch Yard/06/E&C dated February 24, 2006 | 12
12.3 | Transformers | 250 | 317.28 | 1 | [8 empty] | 25 |  |  |  |  | 225 |  |  |  |  | Hangzhou QRE | RCM/PUR/LOI/Transformers/06 dated April 20, 2006 | 261.16 |  | Shanghai Leichun | RCM/PUR/ORDER/transformers/06/E&C dated April 20, 2006 | 56.12
13 | Plant Electricals | 530 | 597.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 87.5 | 87.5 | 87.5 | 111.5 | 75 | 0 | 0 | 0
13.1 | LT Panels | 200 | 177.22 | 1 | [9 empty] | 30 |  | 35 | 35 | 35 | 35 | 30 |  |  | Milestone | RCM/PO/06/Ltcont/01 dated Septmeber 25, 2006 RCM/PO/06/Ltcont/01 dated Septmeber 25, 2006 | 177.22
13.2 | VFD Panels | 100 | 88.92 | 1 | [9 empty] | 15 |  | 17.5 | 17.5 | 17.5 | 17.5 | 15 |  |  | Danfoss | RCM/PO/06/VFD/01 dated October 18, 2006 | 88.92
13.3 | DG Set | 30 | 0 | 1 | [9 empty] | 6 |  |  |  |  | 24 |  |  |  | 0
13.4 | Power Cables | 100 | 153.4 | 1 | [9 empty] | 15 |  | 17.5 | 17.5 | 17.5 | 17.5 | 15 |  |  | Gemscab | RCM/PO/06/Instru. & Elect. Cable/01 dated September 27, 2006 DCM/PUR/ORDER/LT Cables/07 dated February 8, 2007 RCM/PUR/ORDER/LT Cables/06 dated August 14, 2006 | 153.4
|  |  | 36.15 | [19 empty] | Polycab | RCM/PUR/ORDER/HT Cables/06 dated June 24, 2006 | 36.15
13.5 | LT Contract Package | 100 | 141.45 | 1 | [9 empty] | 15 |  | 17.5 | 17.5 | 17.5 | 17.5 | 15 |  |  | Milestone | RCM/PO/06/Ltcont/01 dated Septmeber 25, 2006 | 108.5 |  | Espee Engineering | RCM/PO/06/LtcontErection/01 dated Septmeber 25, 2006 | 32.95
14 | Instrumentation | 200 | 123.68 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 70 | 70 | 0 | 20 | 0 | 0
14.1 | DCS Package | 150 | 96.19 | [11 empty] | 30 |  |  | 52.5 | 52.5 |  | 15 |  | Honeywell | RCM/PUR/ORDER/DCS/06 dated May 30, 2006 | 96.19
14.2 | BOP Instrumentation Package | 50 | 27.49 | [11 empty] | 10 |  |  | 17.5 | 17.5 |  | 5 |  | EPS Instrumentation | RCM/PO/06/Erection & Instrumentation/01 dated September 27, 2006 | 27.49
15 | Insulation | 10 |  | 1 | [14 empty] | 5 | 5 |  |  | Lloyds | RCM/ORDER/Flase-Ceiling & Flooring/06 dated December 25, 2006 | 25.73 |  | Lloyds | RCM/ORDER/Erection of Flase-Ceiling & Flooring/06 dated December 25, 2006 | 6.18
16 | Plant Communication System | 10 |  | 1 | [13 empty] | 5 | 5 |  |  |  | 0
17 | Pumps |  | 19.14 | [19 empty] | Flowmore | DSL/PUR/Order/Pump Set/06 dated September 20, 2006 | 19.14
18 | Cooling Tower |  | 17.31 | [19 empty] | Paharpur | RCM/PUR/Order/Cooling Tower/06 dated July 28, 2006 | 16.3 |  | Paharpur | RCM/PUR/Order/Cooling Tower/E&CC/06 dated September 11, 2006 | 1.01
| Total Power | 7106.2462 | 7276.04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 672.3281 | 321.6 | 68.4112 | 138.7001 | 363.2577 | 431.3953 | 500.4423 | 823.7762 | 656.3487 | 1906.8201 | 712.2833 | 510.8832 | 0
| Contingencies @5% | 103
| (B) Civil Work & Buildings | [21 empty] | 0
1 | Main Plant Area | 600 | 520.2 | 1 | [18 empty] | Amcon | RCM/WO/Civil works/Ramgarh/06 dated March 20, 2006 | 520.2
2 | Other Plant Buildings (S N Mishra) | [21 empty] | 0
3 | Miscellaneous Works (Konark) | [21 empty] | 0
4 | RCC Chimney | 64.5 | 64.5 | [19 empty] | Macro Marvel | RCM/WO/Chimney-Ramgarh/06 dated March 25, 2006 | 64.5
5 | Cement |  | 40 | 1 | [18 empty] | Maihar Cement | RCM/PUR/Order/Cement/06 dated March 21, 2006 | 40
6 | Reinforcement Steel |  | 42.83 | 1 | [18 empty] | Badrinarayan | RCM/PUR/LOI/TMT-SBASL/06 dated June 8, 2006 | 42.83
7 | Structural Steel |  | 21.56 | 1 | [18 empty] | Mahamaya Steel | RCM/PUR/Order/Mahamaya-Strs/06 dated November 15, 2006 | 21.56
8 | Sheeting |  | 5.25 | 1 | [18 empty] | Multicolour | RCM/PUR/ORDER/Sheets/06 November 30, 2006 | 5.25
| Total Civil | 600 | 694.34 | [9 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  |  | 0
| Contingencies @5% | 30
| (C) Others | [21 empty] | 0
1 | Land |  | 0 | [19 empty] | 0
2 | Mechanical Erection Package (Client Supply Items) | 10 | 10 | 1 | [13 empty] | 2.5 | 2.5 | 2.5 | 2.5 |  | 0
3 | Sugar/ Molasses/Bagasse Weighbridge | [8 empty] | 0 |  |  | 0 | 0 | [8 empty] | 0
4 | Misc Fixed Assets |  | 0 | 1 | [18 empty] | 0
| Total Other | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0
| Contingencies @5% | 0.5
| (D) Pre-operative Expenses | [21 empty] | 0
1 | Consultancy
1.1 | Avant Garde (Power Plant)
1.2 | Avant Garde (Civil of Power Plant)
2 | Studies
2.1 | Transmission Line
2.2 | Environmental Studies
2.3 | Soil Investigation
2.4 | Contour Survey
3 | DG Running
4 | Administrative Overheads (Salaries, Wages, Travel)
5 | Miscellaneous
| Total Pre-operative | 100 | 193 |  |  | 4.19 | 6.19 | 9.28 | 5.06 | 3.18 | 0.28 | 6.99 | 6.483 | 6.483 | 6.483 | 6.483 | 6.483 | 6.483 | 6.483 | 6.483 | 6.483 | 6.483 | Details attached |  |  | 5
| (E) Total Cost | 7816.2462 | 8163.38 |  | 0 | 4.19 | 6.19 | 9.28 | 5.06 | 3.18 | 672.6081 | 328.59 | 149.8942 | 220.1831 | 444.7407 | 512.8783 | 581.9253 | 907.7592 | 740.3317 | 1990.8031 | 721.2663 | 517.3662 | 0
| Contingencies @5% | 133.5 | [11 empty] | 4.4287 | 8.9454 | 10.3159 | 11.7047 | 18.2584 | 14.8908 | 40.0425 | 14.5074 | 10.4062 | 0
| (F) Total Plant Cost with Contingencies | 7949.7462 | 8163.38 |  | 0 | 4.19 | 6.19 | 9.28 | 5.06 | 3.18 | 672.6081 | 328.59 | 149.8942 | 224.6118 | 453.6861 | 523.1942 | 593.63 | 926.0176 | 755.2225 | 2030.8456 | 735.7737 | 527.7724 | 0
| IDC | 114.2487 | 244 |  | 0 | 0.22347 | 0.3095 | 0.43307 | 0.21927 | 0.1272 | 24.6623 | 10.953 | 4.4968 | 5.9896 | 10.586 | 10.4639 | 9.8938 | 12.3469 | 7.5522 | 13.539 | 2.4526 | 0 | Details attached |  |  | 6
| (G) Total Cost with IDC | 8063.9948 | 8407.38
| Margin Money | 98 | 98
| (H) Total Cost with Margin Money & IDC | 8161.9948 | 8505.38
Note on C42: Pankaj Rastogi: 3.367% Service Tax
Note on N5: Pankaj Rastogi: 10% advance
Note on N6: Pankaj Rastogi: 10% advance
Note on P5: Pankaj Rastogi: 80% amount in six months
Note on P6: Pankaj Rastogi: 80% amount in six months
Note on W5: Pankaj Rastogi: 10% on commissioing
Note on W6: Pankaj Rastogi: 10% on commissioing