## English
Date |  |  | Action | Note | The number of evidence which will be provied
Year | Month | Day
2001 | 3 | 23 | A study of Taebaek wind resource | ~02.07.31
2003 | 1
| 2 | 28 | 2003 Local Energy Project Plan | Economic evaluation with CERs | 1
3
4
| 5 | 15 | Mt.Maebong wind Park Development-Operational Plan | Decide to proceed the project as a CDM | 2
|  | 23 | A publicd hearing of the Taebaek wind power project
6
7
8
9
10
| 11 | 13 | Noticing Internet News about Taebaek wind power project | Kyunghang newspaper
|  | 26 | Starting of the first stage construction(850kW * 2) | ~04.12.03
12
2004 | 1
2
3
4
5
6
7
| 8 | 30 | Starting of the second stage construction(850kW * 3) | ~05.08.16
9
10
11
| 12 | 3 | Completing of the first stage construction |  | 3
10
2005 | 1
2
3
4
5
| 6 | 25 | Completing of the second stage construction |  | 4
| 7 | 27 | Starting of the last stage construction(850kW * 3) | ~06.11.06
8
9
10
11
12
2006 | 1
2
3
4
5
6
7
8
9
10
| 11 | 6 | Completing of the last stage construction |  | 5
|  |  | Contact of CDM Consulting company | Proposal from cosulting company
12
2007 | 1
| 2 | 22 | A meeting for proceeding the CDM project with KEMCO & Teabaek City Hall | ~07.02.23 | 6
| 3 | 27 | A meeting for MOU with KEMCO & Teabaek City Hall |  | 7
4
| 5 | 2 | A Contract for CDM consulting between KEMCO and ECOSIAN CO., Ltd |  | 8
|  | 8 | Starting of writing PDD
| 6 | 20 | A Contract for validation PDD |  | 9
| 7 | 21 | Receiving public comments | ~07.08.19
|  | 30 | DOE Site review | ~07.07.31
8
9
10
11
| 12 | 6 | Receiving MOC
|  | 31 | Receiving approval of CDM project from the republic of Korea
2008 | 1
2
| 3 | 28 | Complete the PDD
| 4 | 1 | Complete the validation report
5
6
| 7 | 23 | Request for Registration INCOMPLETE from UNFCCC
| 8 | 26 | Request for Review from UNFCCC CDM EB
9